## LINE-Based Sales Reporting Syst
Scope of Work | Team | Job Grade | Manday | Rate | Total | Remark
Assessment Phase
- Analyze LINE Shopping API documentation and data structure. |  |  | 1 | 2500
- Design Database Schema (Orders, Customers, Media Links, Status). |  |  | 1 | 2500
- Design User Flow for Admin (Approval) and Field Staff (Upload). |  |  | 1 | 2500
Backend & API Integration (Ingestion)
- Develop cron job/script to pull "Daily Paid Orders" from LINE Shop API. |  |  | 2 | 2500
- Store order details (order No, Customer LINE ID, Package Type) in the database. |  |  | 1 | 2500
- Error handling for API rate limits and data sync issues. |  |  | 2 | 2500
Web App Development (Staff & Admin Portal)
- Implement Authentication System (Login/Logout, Session Management). |  |  | 2 | 2500
- Staff View: Create mobile-responsive page to view "Pending" orders. |  |  | 3 | 2500
- Admin View: Dashboard to review uploaded clips and click "Approve". |  |  | 3 | 2500
- Upload Module: Integrate QR Scanner/Camera access to record/upload video proof directly to cloud storage (e.g., AWS S3/Google Drive). |  |  | 2 | 2500 |  | May include for Google Drive storage costs for the client to look after
- Implement frontend video compression and resumable upload handling (to prevent timeouts). Might need to use S3 Bucket compatible with IOS |  |  | 1 | 2500
Automation & Notification | [5 empty] | P'Aor provides LINE Official Account (OA) with API rights
- Integrate LINE Messaging API (Push Message). - Logic: Trigger message sending automatically when Admin status = "Approved". - Send Merit Certificate (Image) and Video Link to the specific customer. |  |  | 2 | 2500
Testing & Deployment
- UAT: Test full flow (Buy -> Sync -> Upload -> Approve -> Receive). |  |  | 2 | 2500
- Deploy to production server/cloud environment. |  |  | 1 | 2500
- Handover documentation (User Manual for Admin/Staff
Post-Deployment & Maintenance | [5 empty] | charge 5000 baht once just for the maintenance.
- Storage Management: Implement script to archive or delete videos older than 30/60 days to reduce cloud costs.
- API Token Management: Monitor and rotate LINE API Access Tokens (Long-lived tokens often need refreshing), maybe once every 2 months
|  |  | 24 | 35000
10%